# Project Planning Phase

## Project Planning Template (Product Backlog, Sprint Planning, Stories, Story Points)

Date:07/03/2026

Team ID: SWTID-2026-8514

Project Name:product inventory management system

Maximum Marks
5 Marks

# Product Backlog, Sprint Schedule and Estimation

The following table represents the product backlog and sprint planning details of the project. Each sprint contains specific development tasks along with their estimated story points, priority level, and assigned team member.

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Backend Setup | USN-1 | Set up the Node.js project and configure the Express server | 6 | High | Avaneesh |
| Sprint-1 | Database Setup | USN-2 | Establish connection with MongoDB Atlas and design the database structure | 6 | High | Avaneesh |
| Sprint-1 | User Model | USN-3 | Develop the User schema and implement password hashing | 8 | High | Avaneesh |
| Sprint-2 | JWT Authentication | USN-4 | Create register and login APIs using JWT token authentication | 8 | High | Avaneesh |
| Sprint-2 | Auth Middleware | USN-5 | Develop middleware for verifying JWT tokens and protecting routes | 6 | High | Avaneesh |
| Sprint-2 | Product Model | USN-6 | Create Product schema and link it with the userId | 6 | High | Avaneesh |
| Sprint-3 | Product CRUD APIs | USN-7 | Implement APIs for adding, retrieving, updating, and deleting products | 10 | High | Avaneesh |
| Sprint-3 | Search API | USN-8 | Develop API endpoint for product search and filtering | 6 | Medium | Avaneesh |
| Sprint-3 | Authorization Logic | USN-9 | Ensure users can access and manage only their own products | 6 | High | Avaneesh |
| Sprint-4 | Error Handling | USN-10 | Implement centralized middleware for handling application errors | 6 | Medium | Avaneesh |
| Sprint-4 | API Testing | USN-11 | Perform API testing using Postman and verify responses | 5 | Medium | Avaneesh |
| Sprint-4 | Backend Optimization | USN-12 | Improve API performance and implement validation checks | 5 | Medium | Avaneesh |

# Project Tracker, Velocity & Burndown Chart

The following table summarizes the sprint schedule, estimated story points, and completion details for each development sprint.

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 20 | 5 Days | 17 Feb 2026 | 21 Feb 2026 | 20 | 21 Feb 2026 |
| Sprint-2 | 20 | 5 Days | 22 Feb 2026 | 26 Feb 2026 | 20 | 26 Feb 2026 |
| Sprint-3 | 22 | 5 Days | 27 Feb 2026 | 3 Mar 2026 | 22 | 3 Mar 2026 |
| Sprint-4 | 16 | 4 Days | 4 Mar 2026 | 8 Mar 2026 | 16 | 8 Mar 2026 |